## Sheet1
Upgrade Windows Checklist
| Name: | Client SUNet ID:
| Phone #: | Department:
| Ac Adapter: | Loaner:
| Hostname: | New Hostname:
| Intake Date: | Due Date:
| Notes | Accesories:
User drop-off steps:
☐ | Verify ITS Account is accessible
☐ | Verify Backup Software at >99%
Computer setup process:
☐ | Mark Encryption Project Page with the date/time computer was received; Mark Down loaner if issued
☐ | BACKUP PROCESS
☐ | Boot to Genius Drive. Map M:\ to: \\cryptonas\data1 (or data2); Run backup.bat
☐ | Show hidden files & copy user profile folder to USMT folder on NAS; search root directory for files
☐ | Run Ghost11 and create image of disk to folder created earlier by script
☐ | IMAGE PROCESS
☐ | Setup NetDB Node and Name (Radis will name computer based off NetDB Node Name)
☐ | RaDIS with Windows 7 Enterprise
☐ | Verify Absolute Manage client installed; install from Post RaDIS folder on its desktop, if absent
☐ | Perform Updates (Windows Updates, Sophos, Adobe etc)
☐ | Perform USMT_Restore.
☐ | While data is transferring, contact user with status update
☐ | Move Computer to proper AD Organizational Unit
☐ | Install custom applications, drivers and printers (Remove Adobe Reader if installing Acrobat)
☐ | Confirm Office Service Pack 3 & Zimbra Outlook Connector are installed
☐ | Confirm Windows is activated
☐ | Confirm user is added to local 'Administrator' and 'Sophos Administrator' group
☐ | Set “Stanford” wireless to ‘connect automatically’
☐ | ENCRYPTION PROCESS
☐ | Enable TPM in Bios. Ensure proper TPM driver installed in Device Manger
☐ | Run SWDE installer and prepare system for encryption; Encrypt Drive
☐ | Contact user that computer is ready for pickup.
☐ | Add computer's new host name to Encryption Project Page; (Dept)-(Serial Number)
☐ | Print and affix label with new host name
☐ | Update hostname in NetDB record
User return steps:
☐ | Have user log in to computer, load Outlook and confirm access to email
☐ | Confirm user's printers and network drives; have user confirm files and web browser data (favorites, etc)
☐ | Open Backup Software, if not working advise; if not installed, setup Mozy.
☐ | (Win) Have user set up BitLocker pin & backup to flash drive
☐ | Reboot computer and confirm user can log in using encryption.
☐ | Receive loaner from user, reset Bit Locker pin and delete user profile
Final completion steps:
☐ | Mark Encryption Project Page that computer encryption has been completed, and any other required fields.